## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | karamjeet kaur 23808847
As a user, I want:
|  | No | User stories
|  | 1 | snake eat prey
|  | 2 | snake color
|  | 3 | snake movement
|  | 4 | snake growth
|  | 5 | prey shape
|  | 6 | prey color
|  | 7 | prey change location
|  | 8 | gameboard color
|  | 9 | gameboard resizeable
|  | 10 | gameboard exit

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | karamjeet kaur 23808847
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2 |  | 10%
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard
3.1.2 |  |  | GUI for login form |  | 100%
0
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic |  |  | 30%
3.2.2 |  |  | snake color
3.2.3 |  |  | snake growth
3.2.4 |  |  | snake eat prey
3.2.5 |  |  | prey change direction
3.2.6 |  |  | prey color
3.2.7 |  |  | prey shape
3.2.8 |  |  | gameboard resizeable
3.2.9 |  |  | gameboard color
gameboard exit
4 | Test and deploy the game |  |  | 3 | 10%
| login form |  |  |  | 100%
5 | Document the game |  |  | 4 | 0%